## Qualitative Risks
Risk |  |  | Pre-mitigation |  |  |  |  | Response |  |  | Post-mitigation |  |  |  |  | Details
ID | Type | Title | Probability | Schedule | Cost | Performance | Score | Strategy | Title | Total Cost | Probability | Schedule | Cost | Performance | Score | Owner | Description | Cause | Effect | Category | Trigger | Status | Proximity | Start Date | End Date | Exposure/EMV | Quantifiable Risk | Notes
R001 | Threat | Financial concerns | VH | VH | H | H | 80 | Mitigate | Obtain financing from private credit facilities that stand to gain from the projects | NA | H | H | L | M | 30 | Project manager | Inability to obtain commitments for the full amount of the required term loans | Due to India’s subdued market conditions combined with the high leverage of the projects | Inadequate funding could cause a delay in project kick-off | cost/schedule | Funding raised is insufficient to start the project | Open | Overdue | 2009-02-20 | 2009-08-15 | NA | TRUE | NA
R002 | Threat | Pollution control approvals | H | H | VH | M | 70 | Mitigate | Apply for pollution control approvals early and adhere to all pollution control standards | 25000 | H | H | L | H | 30 | Utilities manager | Inability to obtain approvals for pollution control | Due to the volume experienced by both the state and federal ministiries | Extended project duration | cost/schedule | Approvals not granted | Open | Overdue | 2009-03-01 | 2009-05-21 |  | TRUE | Tmely approvals from both the state and federal ministries permits early project kick-off
R003 | Threat | Arrival of fully assembled components | H | VH | L | M | 75 | Mitigate | Order parts early and pay expedite fee | 250000 | M | H | H | N | 20 | Equipment engineering | Due to global supply chain difficulties, critical parts of the power plants could arrive late | Due to difficulties in global supply chain | Delay in assembling and installing the power plant | project/business/schedule | Vendor quotes extended lead time | Open | Mid Term | 2010-07-15 | 16 Sept 2010 | 700000 | TRUE | Container ships carrying critical parts are constantly waiting at the port
R004 | Threat | Coal shipments | M | H | H | H | 60 | Mitigate | Obtain coal from local vendors | 500000 | L | M | H | H | 25 | Project manager/ operations manager | Delay in the importation of coal on which the project initiatives would run | Due to complications on port, road or rail transportation networks | Indefinite suspension of the running of the power plants | project/business/cost | Vendor quotes extended lead time | Proposed | Distant | 2012-08-30 | 2012-12-01 | 1000000 | TRUE | It is mandatory that appropriate mechanisms are employed to reduce the deterioration of air quality
R005 | Threat | Controlling carbon emissions | H | H | VH | M | 70 | Mitigate | Invest in technologies that break down carbondioxide and release oxygen into the atmosphere | 300000 | H | H | H | H | 25 | Safety manager | Inability of improved technology to control carbon emissions | Due to uncontrollable carbon emissions | Regulatory bodies could suspend the construction of the power plants | project/ cost/schedule | Uncontrollable carbon emissions | Proposed | Mid Term | 30 Sept 2010 | 2011-03-02 | 400000 | FALSE | Brainstorming and intensive research must be carried out with regards to the control of carbon emissions
R006 | Threat | Unfinished contracts | L | M | M | L | 60 | Mitigate | Employment of contractors who are competent and agree to the company's terms and conditions | 30000 | L | L | L | M | 35 | project manager/HR | The use of contract packages for the construction of the power plants leading to unfinalized agreements | Due to the use of package contracts | Cost overrun | cost/schedule | Contractors not in agreement of company's terms and conditions | Open | Imminent | 2009-10-01 | 2010-04-02 | 50000 | TRUE | Contractors must be in alignment with the company's terms and conditions so as not to prolong project duration
R007 | Opportunity | Adequate land mass | H | VL | H | N | 60 | Exploit | Request land needed from parent company | NA | M | H | VL | H | 10 | Executive leadership | Parent company owns sufficient land mass that can be used for the project | Ownership of sufficient land mass | Cost-effective and time-effective | cost/schedule | Need to acquire land for the projects | Open | Imminent | 2009-10-01 | 2009-12-01 | NA | FALSE | The availability of land enables the project team focus on other important matters
R008 | Opportunity | Institutions both residential and business | H | L | H | N | 50 | Accept |  | NA | [5 empty] | Executive leadership | The location of the land on which the power plant will be constructed has low proximity to residential and commercial institutions | Due to the low proximity of the power plant's location to residential areas | Speedy construction of power plants, reduced destuction of life and property | schedule/business | Production of toxic substances | Proposed | Mid Term | 2010-08-01 | 2012-04-30 |  | FALSE | The low proximity of project's location to residential ares can speed up granting of approvals
R009 | Threat | Breakdowns in mechanical and electrical systems | M | M | M | H | 30 | Mitigate | Use predictive analytics and condition monitoring systems to forecast when failures might occur | 15000 | H | VH | L | H | 15 | Director of engineering | Using predictive analytic tools to forecast when mechanical/ electrical failures might occur | Defects in machinery and plants | Disruption of operations and extension of project schedule | Implementation/schedule | Defects in plants and machinery | Rejected(Closed) | Imminent | 2009-11-01 | 2010-05-12 | 30000 | FALSE | Defects in machinery must be detected to prevent systems malfuction or failure
R010 | Threat | Insufficient fuel extraction | L | VL | L | L | 20 | Transfer | Connect with local extraction mines to provide fuel needed | 20000 | H | H | L | M | 15 | Extractions manager | Insufficient fuel extracted from the soil for the Dharnavaram plant | insufficient fuel in the mines | Delay in project implementation | implementation | Exhaustion of fuel in the mines | Managed(Closed) | Distant | 2012-01-01 | 2012-04-30 | 50000 | FALSE | The project manager in liaison with the extractions manager are currently getting in contact with local minning industries
R011 | Threat | Community assistance | H | VH | L | L | 70 | Mitigate | Engage with community stakeholder in townhalls to understand their concerns | 80000 | M | H | M | N | 40 | Executive leadership | Arrange townhall meetings with community members to understand their concerns and inform them about the benefits thery stand to enjoy from the project | Lack of community support | Delay in project schedule | schedule/implementation | Lack of community support | Impacted(Closed) | Overdue | 2009-06-01 | 2009-10-01 | 50000 | FALSE | The project leadership and other relevant stakeholders have devised a plan to hold multiple townhall meeting to gather community support for the project
R012 | Threat | Working circumstances are hazardous. | H | M | VH | VH | 80 | Mitigate | Provide an on-site doctor and do regular check-ups for the workers | 50000 | H | VH | M | VH | 45 | Project manager/safety manager |  | Due to unfavorable weather conditions and lack of appropriate tools | Extended project duration | cost/schedule | Lack of required tools and Machines | Open | Mid Term | 2010-06-16 | 2010-12-16 | 45000 | TRUE | Tools and machinery must be made available on site
R013 | Threat | Construction weather conditions | VH | VH | H | VH | 80 | Mitigate | Weather conditions are inevitable and can only be tackled by ensuring safety of everyone on-site and increasing working hours to meet the schedule deadline | 20000 | M | H | L | H | 30 | Weather station manager | Clear the construction site and try start work when the weather is good or medium. | Due to unfavorable weather conditions | Extended project duration | schedule/implementation | Unfavorable weather conditions | Managed(Closed) | Mid Term | 2010-02-16 | 2010-11-20 | 45000 | FALSE | It is imperative that the risk owner closely monitors weather forecasts and report to get ahead of any challenges that may occur as a result of unfavorable weather conditions
R014 | Threat | Fuel price fluctuation | H | L | VH | L | 60 | Transfer | Long-term contracts with set pricing with suppliers | 25000 | M | L | H | L | 20 | Human Resources manager | Fuel price fluctuations put the power plant's functioning at risk due to instable variable costs. A power plant may be exposed to environmental hazards related with fuel management and storage. | Due to increment in the costs of resources | Cost overrun | Cost | Increase in price of fuel | Managed(Closed) | Mid Term | 2010-02-25 | 2010-11-25 | 50000 | TRUE | Flunctuations in fuel price is inevitable, as such, increse in the cost of fuel is likely to affect total cost of the project
R015 | Threat | Using low-cost technical components | M | H | VH | H | 50 | Avoid | Utilization of standard Information systems components that are easy to replace | 10000 | M | H | M | H | 20 | IT manager | Power plants may face operational risk as a result of failure owing to technical novelty, failure of panels as well as other components, or loss of efficiency, all of which can result in unplanned energy generation downtime. | Due to technological component failure | Delay in construction and increase in cost | cost/schedule | Breakdown of cheap technological parts used for construction | Proposed | Mid Term | 2011-01-01 | 2011-08-06 | 30000 | TRUE | The use of cheap technological parts may slow down project implementation
R016 | Threat | Relocation of Utilities | VL | H | H | M | 30 | Avoid | Have construction vehicles on standby for any relocation of resources | 10000 | M | H | VH | H | 15 | Utilities manager | Locations of certain utilities are unknown and their relocation could be required | Due to the unknown locations of utilities | Disruption in project implementation | implementation | unknown location of utilities | Impacted(Closed) | Mid Term | 2010-08-17 | 2010-12-01 | 10000 | FALSE | Known location of utilties aids easy track of supplies needed for construction
R017 | Threat | Administrative Fees for Grantees | H | L | M | L | 45 | Avoid | Increase working hours on the construction site if for any reason the project is running behind schedule | 5000 | M | H | VL | H | 20 | Admin manager/financial manager | Factors such as supply chain, on-site delays, document misplacements, etc. will be responsible for this risk. |  |  |  |  | Proposed | Imminent | 2010-08-11 | 2010-11-12 | 20000 | TRUE | It is mandatory to maintain time schedules and proper supply of materials required for the project

## Response Actions
Mitigation Details |  |  |  | Task/Work Details | [7 empty] | Post-Mitigation Position
Name | Risk ID | Description | Responsibility | Start | Finish | Target Start | Target Finish | Mitigation Cost | Actual Cost | Task/WBS | Status | Probability | Schedule | Cost | Performance | Score
Financial concerns | R001 | Inability to get full commitments for the requisite term loans | Project manager | 2009-02-20 | 2009-08-15 | 2009-02-10 | 2009-08-01 | NA | 15000 | 2.3.1 | Complete | H | H | L | M | 30
Pollution control approvals | R002 | Inability to receive approvals for pollution control | Utilities manager | 2009-03-22 | 2009-05-21 | 2009-03-01 | 2009-05-10 | 25000 | 30000 | 2.3.2 | Complete | H | H | L | H | 30
Arrival of fully assembled components | R003 | Critical elements of power plants may arrive late due to global supply chain issues | Equipment engineering | 2010-07-15 | 16 Sept 2010 | 2010-07-02 | 10 Sept 2010 | 250000 | 260000 | 3.1.1 | Proposed | M | H | H | N | 20
Coal shipments | R004 | Importation of coal, which the project initiatives rely on, is delayed. | Project manager/ operations manager | 2012-08-30 | 2012-12-01 | 2012-08-15 | 2012-12-25 | 500000 | 400000 | 2.7.3 | Proposed | L | M | H | H | 25
Controlling carbon emissions | R005 | Invest in carbon-dioxide-breaking technology that release oxygen into the environment | Safety manager | 30 Sept 2010 | 2011-03-02 | 20 Sept 2010 | 2011-03-01 | 300000 | 250000 | 2.6.2 | Proposed | H | H | H | H | 25
Unfinished contracts | R006 | Employment of contractors who are competent and agree to the company's terms and conditions | Project manager/ Human Resources | 2009-10-01 | 2010-04-02 | 2009-10-01 | 2010-03-26 | 30000 | 35000 | 2.3.6 | Complete | L | L | L | M | 35
Adequate land mass | R007 | Request land required from parent firm | Executive leadership | 2009-10-01 | 2009-12-01 | 26 Sept 2009 | 2009-12-27 | NA | 2000000 | 2.7.1 | Complete | M | H | VL | H | 10
Institutions both residential and business | R008 |  | Executive leadership | 2009-08-01 | 2010-04-30 | 2009-07-29 | 2010-04-01 | NA | 80000 | 2.6.1 | Proposed
Breakdowns in mechanical and electrical systems | R009 | Use predictive analytics and condition monitoring systems to forecast when failures might occur | Director of Engineering | 2009-11-01 | 2010-05-12 | 2009-11-01 | 2010-05-12 | 15000 | 15000 | 4.2.4 | Rejected | H | VH | L | H | 15
Insufficient fuel extraction | R010 | Make contact with local extraction mines to provide fuel needed | Extractions manager | 2012-01-01 | 2012-04-30 | 2012-01-01 | 2012-04-30 | 20000 | 20000 | 3.6.1 | InProgress | H | H | L | M | 15
Community assistance | R011 | Interact with community stakeholder in townhalls to discover their concerns | Executive leadership | 2009-06-01 | 2009-10-01 | 2009-05-01 | 25 Sept 2009 | 80000 | 80000 | 1.3.1 | InProgress | M | H | M | N | 40
Working circumstances are hazardous. | R012 | Due to weather condition and lack of appropriate tools | Project manager/ safety manager | 2010-06-16 | 2010-12-16 | 2010-06-05 | 2010-12-15 | 50000 | 50000 | 2.6.4 | InProgress | H | VH | M | VH | 45
Construction weather conditions | R013 | We may have to reschedule the construction work many times due to weather conditions. | Weather stations manager | 2010-02-16 | 2010-11-20 | 2010-02-10 | 2010-11-01 | 20000 | 25000 | 4.5.1 | InProgress | H | H | L | H | 30
Fuel price fluctuation | R014 | Long-term contracts with set pricing with suppliers can be utilized to shift part or all of the fuel price risk. | Financial Officer/Accounts Manager | 2010-02-25 | 2010-11-25 | 2010-02-20 | 2010-11-20 | 25000 | 24000 | 2.8.3 | Proposed | VL | L | H | L | 20
Using low-cost technical components | R015 | The risk of operation disruption because of component failure can be reduced by utilizing standard components that are easy to replace. | Technical Engineer | 2011-01-01 | 2011-08-06 | 2010-12-30 | 2011-07-31 | 10000 | 10000 | 2.7.3 | Proposed | M | H | M | H | 20
Relocation of Utilities | R016 | External factors and many internal variables such as availability of space on the construction site will come into effect. | Utilities manager | 2010-08-17 | 2010-12-01 | 2010-08-05 | 2010-11-17 | 10000 | 10000 | 2.7.5 | InProgress | M | H | VH | H | 15
Administrative Fees for Grantees | R017 | Factors such as supply chain, on-site delays, document misplacements, etc. will be responsible for the risk | Admin manager/ Financial manager | 2010-08-11 | 2010-11-12 | 2010-08-01 | 2010-11-01 | 5000 | 5000 | 2.2.4 | InProgress | M | H | H | H | 20

## Quantitative Risks
Scenario Name | ID | Title | Probability | Mitigation Cost | Mitigation Time | Mitigation Actions
Pre-Mitigation | R001 | Financial concerns | 80% | 25000 | 6months | Obtain finance from private credit facilities that have a vested interest in the project.
Pre-Mitigation | R002 | Pollution control approvals | 70% | 25000 | 2months | Apply for pollution control approvals early and adhere to all pollution control standards
Pre-Mitigation | R003 | Arrival of fully assembled components | 75% | 250000 | 2months | Order parts ahead of time and pay an expedite cost.
Pre-Mitigation | R004 | Coal shipments | 60% | 500000 | 3months | Purchase coal from a local merchant.
Pre-Mitigation | R005 | Controlling carbon emissions | 70% | 300000 | 7months | Invest in technology that decompose CO2 and release oxygen into the environment.
Pre-Mitigation | R006 | Unfinished contracts | 60% | 30000 | 6months and 1days | Employing skilled contractors who agree to the company's terms and conditions
Pre-Mitigation | R007 | Adequate land mass | 60% | NA | 2months | Request land from the parent firm.
Pre-Mitigation | R008 | Institutions both residential and business | 50% | NA | 9months | Request to get permission for Residentails and comercial use
Pre-Mitigation | R009 | Breakdowns in mechanical and electrical systems | 30% | 15000 | 6months and 12days | Predictive analytics and condition monitoring systems can be used to predict when breakdowns will occur.
Pre-Mitigation | R010 | Insufficient fuel extraction | 20% | 20000 | 4months | Connect with local extraction mines to supply needed fuel.
Pre-Mitigation | R011 | Community assistance | 70% | 80000 | 4months | Organize town hall meetings with community people to learn about their concerns and to tell them about the benefits of the project.
Pre-Mitigation | R012 | Working circumstances are hazardous. | 80% | 50000 | 6months | Because of the weather and a lack of appropriate tools.
Pre-Mitigation | R013 | Construction weather conditions | 80 | 20000 | 9months | We have to reschedule the construction work due to weather conditions on occasion.
Pre-Mitigation | R014 | Fuel price fluctuation | 60% | 25000 | 9months | Long-term contracts with suppliers that have predetermined pricing can be used to move some or all of the fuel price risk.
Pre-Mitigation | R015 | Using low-cost technical components | 50% | 10000 | 7months and 6days | The danger of operation disruption due to component failure can be avoided by using standard, easily replaceable components.
Pre-Mitigation | R016 | Relocation of Utilities | 30 | 10000 | 4months and 17days | Make adequate storage and on-site space for construction equipment.
Pre-Mitigation | R017 | Administrative Fees for Grantees | 45 | 5000 | 3months | Increase construction site working hours if the project is falling behind schedule for any reason.

## Task Impacts
|  |  | Schedule |  |  |  | Cost
Scenario Name | Risk ID | WBS/Task ID | Shape | Minimum | Likely | Maximum | Cost Shape | Cost Minimum | Cost Likely | Cost Maximum
Pre-mitigation | R001 | 2.3.1 | Triangle | 4months | 6months | 6months | Triangle | 0 | 25000 | 30000
Pre-Mitigation | R002 | 2.3.2 | Uniform | 2months | 2months | 3months | Uniform | 20000 | 25000 | 35000
Pre-Mitigation | R003 | 3.1.1 | Uniform | 2months | 2months | 3months | Triangle | 250000 | 250000 | 270000
Pre-Mitigation | R004 | 2.7.3 | Triangle | 3months | 3months | 4months | Uniform | 450000 | 500000 | 500000
Pre-Mitigation | R005 | 2.6.2 | Uniform | 5months | 7months | 9months | Uniform | 300000 | 300000 | 350000
Pre-Mitigation | R006 | 2.3.6 | Uniform | 5months | 6months and 1days | 7months | Triangle | 20000 | 30000 | 40000
Pre-Mitigation | R007 | 2.7.1 | Triangle | 1month | 2months | 2months | Uniform | NA | NA | NA
Pre-Mitigation | R008 | 2.6.1 | Uniform | 8months | 9months | 10months | Uniform | NA | NA | NA
Pre-Mitigation | R009 | 4.2.4 | Triangle | 6months | 6months and 12days | 6months | Triangle | 15000 | 15000 | 20000
Pre-Mitigation | R010 | 3.6.1 | Triangle | 2months | 4months | 5months | Triangle | 19000 | 20000 | 25000
Pre-Mitigation | R011 | 1.3.1 | Uniform | 2months | 4months | 3months | Triangle | 75000 | 80000 | 89000
Pre-Mitigation | R012 | 2.6.4 | BetaPert | 6months | 6months | 6months | Uniform | 47000 | 50000 | 51000
Pre-Mitigation | R013 | 4.5.1 | Triangle | 9months | 9months | 9months | Triangle | 20000 | 20000 | 25000
Pre-Mitigation | R014 | 2.8.3 | Triangle | 8months | 9months | 10months | Uniform | 25000 | 25000 | 35000
Pre-Mitigation | R015 | 2.7.3 | Uniform | 7months | 7months and 6days | 9months | Uniform | 8000 | 10000 | 15000
Pre-Mitigation | R016 | 2.7.5 | Triangle | 3months | 4months and 17days | 5months | Uniform | 5000 | 10000 | 20000
Pre-Mitigation | R017 | 2.2.4 | Triangle | 3months | 3months | 5months | Triangle | 5000 | 5000 | 8000

## Options (hidden)
<Options><IncludeRisksWithScore>false</IncludeRisksWithScore><HiddenColumns Name="untitled"/><IncludeRisksWithScoreNum>0</IncludeRisksWithScoreNum><DefaultShape>3</DefaultShape><MaxVHValue>2.000000</MaxVHValue><SpreadCosts>true</SpreadCosts><SpreadDurations>true</SpreadDurations><CostsIncludeDur>false</CostsIncludeDur><ShowImpactsAsPercent>false</ShowImpactsAsPercent><LinkImpacts>true</LinkImpacts><AutoPopulateTaskImpacts>true</AutoPopulateTaskImpacts><rgbThreat>5992447</rgbThreat><rgbOpportunity>12561751</rgbOpportunity><rgbCurrent>14871722</rgbCurrent><rgbTarget>9602507</rgbTarget><rgbMitigate>16777215</rgbMitigate><rgbEliminate>16777215</rgbEliminate><rgbAccept>16777215</rgbAccept><rgbTransfer>16777215</rgbTransfer></Options>
<UserFieldDefinitions><UserFieldDefinition ID="{E8C40036-8B26-4DC7-82E1-8350F145F83F}"><ID>{E8C40036-8B26-4DC7-82E1-8350F145F83F}</ID><Name>UserText1</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{0D50B242-233B-4A65-B070-AC0D8FE7399E}"><ID>{0D50B242-233B-4A65-B070-AC0D8FE7399E}</ID><Name>UserText2</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{954B7D84-CEB2-449E-BC85-1D67D9533E9D}"><ID>{954B7D84-CEB2-449E-BC85-1D67D9533E9D}</ID><Name>UserText3</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{461E22CD-2DA4-49FD-9F28-A64470A3E363}"><ID>{461E22CD-2DA4-49FD-9F28-A64470A3E363}</ID><Name>UserText4</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{EACF91EF-9082-4492-BFEA-7C9CF6DA3D4E}"><ID>{EACF91EF-9082-4492-BFEA-7C9CF6DA3D4E}</ID><Name>UserText5</Name><Type>Text</Type></UserFieldDefinition><UserFieldTabName>User Defined</UserFieldTabName></UserFieldDefinitions>
<PID><LevelTypes><LevelType Name="Tolerance"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Negligible</FullName><Color>#969696</Color></Level><Level Position="1"><ShortName>L</ShortName><FullName>Low</FullName><Color>#00FF00</Color></Level><Level Position="2"><ShortName>M</ShortName><FullName>Medium</FullName><Color>#FFFF00</Color></Level><Level Position="3"><ShortName>H</ShortName><FullName>High</FullName><Color>#FF0000</Color></Level></Levels></LevelType><LevelType Name="Proximity"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Overdue</FullName><Color>#FF0000</Color></Level><Level Position="1"><ShortName>I</ShortName><FullName>Imminent</FullName><Color>#FF0000</Color></Level><Level Position="2"><ShortName>M</ShortName><FullName>Mid Term</FullName><Color>#FFFF00</Color></Level><Level Position="3"><ShortName>D</ShortName><FullName>Distant</FullName><Color>#00FF00</Color></Level></Levels></LevelType><LevelType Name="Manageability"><Levels><Level Position="0"><ShortName>N</ShortName><FullName></FullName><Color>#FFFFFF</Color></Level><Level Position="1"><ShortName>E</ShortName><FullName>Easy</FullName><Color>#00FF00</Color></Level><Level Position="2"><ShortName>M</ShortName><FullName>Moderate</FullName><Color>#FFFF00</Color></Level><Level Position="3"><ShortName>D</ShortName><FullName>Difficult</FullName><Color>#FF0000</Color></Level></Levels></LevelType><LevelType Name="Impacts"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Negligible</FullName><Color>#FFFFFF</Color></Level><Level Position="1"><ShortName>VL</ShortName><FullName>Very Low</FullName><Color>#FFFFFF</Color></Level><Level Position="2"><ShortName>L</ShortName><FullName>Low</FullName><Color>#FFFFFF</Color></Level><Level Position="3"><ShortName>M</ShortName><FullName>Medium</FullName><Color>#FFFFFF</Color></Level><Level Position="4"><ShortName>H</ShortName><FullName>High</FullName><Color>#FFFFFF</Color></Level><Level Position="5"><ShortName>VH</ShortName><FullName>Very High</FullName><Color>#FFFFFF</Color></Level></Levels></LevelType><LevelType Name="Probability"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Negligible</FullName><Color>#FFFFFF</Color></Level><Level Position="1"><ShortName>VL</ShortName><FullName>Very Low</FullName><Color>#FFFFFF</Color></Level><Level Position="2"><ShortName>L</ShortName><FullName>Low</FullName><Color>#FFFFFF</Color></Level><Level Position="3"><ShortName>M</ShortName><FullName>Medium</FullName><Color>#FFFFFF</Color></Level><Level Position="4"><ShortName>H</ShortName><FullName>High</FullName><Color>#FFFFFF</Color></Level><Level Position="5"><ShortName>VH</ShortName><FullName>Very High</FullName><Color>#FFFFFF</Color></Level></Levels></LevelType></LevelTypes><Tolerance Name="Tolerance"><Thresholds LevelName="Tolerance"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to 5</Description><FullLevelDescription>L (Up to 5)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>5</Value><Description>5 to 23</Description><FullLevelDescription>M (5 to 23)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>23</Value><Description>23 or higher</Description><FullLevelDescription>H (23 or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Tolerance</Name><Order>0</Order><UseImpact>true</UseImpact><Type>Tolerance</Type><LevelType>Tolerance</LevelType></Tolerance><Proximity Name="Proximity"><Thresholds LevelName="Proximity"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>0</Description><FullLevelDescription>I (0)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>60</Value><Description>60</Description><FullLevelDescription>M (60)</FullLevelDescription><Weighting>0.900000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>180</Value><Description>180</Description><FullLevelDescription>D (180)</FullLevelDescription><Weighting>0.800000</Weighting></Threshold></Thresholds><Name>Proximity</Name><Order>0</Order><UseImpact>false</UseImpact><Type>Proximity</Type><LevelType>Proximity</LevelType></Proximity><Manageability Name="Manageability"><Thresholds LevelName="Manageability"><Threshold Level="1"><Level>1</Level><Value>Requires minimal changes to project baseline</Value><Description>Requires minimal changes to project baseline</Description><FullLevelDescription>E (Requires minimal changes to project baseline)</FullLevelDescription><Weighting>1.100000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>Requires some changes to project baseline</Value><Description>Requires some changes to project baseline</Description><FullLevelDescription>M (Requires some changes to project baseline)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>Requires many changes to project baseline</Value><Description>Requires many changes to project baseline</Description><FullLevelDescription>D (Requires many changes to project baseline)</FullLevelDescription><Weighting>0.900000</Weighting></Threshold></Thresholds><Name>Manageability</Name><Order>0</Order><UseImpact>false</UseImpact><Type>User</Type><LevelType>Manageability</LevelType></Manageability><ImpactDefinitions><ImpactDefinition Name="Schedule"><Thresholds LevelName="Impacts"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to 5</Description><FullLevelDescription>VL (Up to 5)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>5</Value><Description>5 to 10</Description><FullLevelDescription>L (5 to 10)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>10</Value><Description>10 to 20</Description><FullLevelDescription>M (10 to 20)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>20</Value><Description>20 to 40</Description><FullLevelDescription>H (20 to 40)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>40</Value><Description>40 or higher</Description><FullLevelDescription>VH (40 or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Schedule</Name><Order>0</Order><UseImpact>true</UseImpact><Type>Schedule</Type><LevelType>Impacts</LevelType></ImpactDefinition><ImpactDefinition Name="Cost"><Thresholds LevelName="Impacts"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to $5,000</Description><FullLevelDescription>VL (Up to $5,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>5,000</Value><Description>$5,000 to $10,000</Description><FullLevelDescription>L ($5,000 to $10,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>10,000</Value><Description>$10,000 to $25,000</Description><FullLevelDescription>M ($10,000 to $25,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>25,000</Value><Description>$25,000 to $50,000</Description><FullLevelDescription>H ($25,000 to $50,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>50,000</Value><Description>$50,000 or higher</Description><FullLevelDescription>VH ($50,000 or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Cost</Name><Order>1</Order><UseImpact>true</UseImpact><Type>Cost</Type><LevelType>Impacts</LevelType></ImpactDefinition><ImpactDefinition Name="Performance"><Thresholds LevelName="Impacts"><Threshold Level="1"><Level>1</Level><Value>Failure to meet a minor acceptance criteria</Value><Description>Failure to meet a minor acceptance criteria</Description><FullLevelDescription>VL (Failure to meet a minor acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>Failure to meet more than one minor acceptance criteria</Value><Description>Failure to meet more than one minor acceptance criteria</Description><FullLevelDescription>L (Failure to meet more than one minor acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>Shortfall in meeting acceptance criteria</Value><Description>Shortfall in meeting acceptance criteria</Description><FullLevelDescription>M (Shortfall in meeting acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>Significant shortfall in meeting acceptance criteria</Value><Description>Significant shortfall in meeting acceptance criteria</Description><FullLevelDescription>H (Significant shortfall in meeting acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>Failure to meet acceptance criteria</Value><Description>Failure to meet acceptance criteria</Description><FullLevelDescription>VH (Failure to meet acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Performance</Name><Order>2</Order><UseImpact>true</UseImpact><Type>User</Type><LevelType>Impacts</LevelType></ImpactDefinition></ImpactDefinitions><Probability Name="Probability"><Thresholds LevelName="Probability"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to 10%</Description><FullLevelDescription>VL (Up to 10%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>10</Value><Description>10% to 30%</Description><FullLevelDescription>L (10% to 30%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>30</Value><Description>30% to 50%</Description><FullLevelDescription>M (30% to 50%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>50</Value><Description>50% to 70%</Description><FullLevelDescription>H (50% to 70%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>70</Value><Description>70% or higher</Description><FullLevelDescription>VH (70% or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Probability</Name><Order>0</Order><UseImpact>true</UseImpact><Type>Probability</Type><LevelType>Probability</LevelType></Probability><Scores><Score Probability="1" Impact="1" Color="#00FF00">1</Score><Score Probability="1" Impact="2" Color="#00FF00">1</Score><Score Probability="1" Impact="3" Color="#00FF00">2</Score><Score Probability="1" Impact="4" Color="#00FF00">4</Score><Score Probability="1" Impact="5" Color="#FFFF00">8</Score><Score Probability="2" Impact="1" Color="#00FF00">2</Score><Score Probability="2" Impact="2" Color="#00FF00">3</Score><Score Probability="2" Impact="3" Color="#FFFF00">6</Score><Score Probability="2" Impact="4" Color="#FFFF00">12</Score><Score Probability="2" Impact="5" Color="#FF0000">24</Score><Score Probability="3" Impact="1" Color="#00FF00">3</Score><Score Probability="3" Impact="2" Color="#00FF00">5</Score><Score Probability="3" Impact="3" Color="#FFFF00">10</Score><Score Probability="3" Impact="4" Color="#FFFF00">20</Score><Score Probability="3" Impact="5" Color="#FF0000">40</Score><Score Probability="4" Impact="1" Color="#00FF00">4</Score><Score Probability="4" Impact="2" Color="#FFFF00">7</Score><Score Probability="4" Impact="3" Color="#FFFF00">14</Score><Score Probability="4" Impact="4" Color="#FF0000">28</Score><Score Probability="4" Impact="5" Color="#FF0000">56</Score><Score Probability="5" Impact="1" Color="#00FF00">5</Score><Score Probability="5" Impact="2" Color="#FFFF00">9</Score><Score Probability="5" Impact="3" Color="#FFFF00">18</Score><Score Probability="5" Impact="4" Color="#FF0000">36</Score><Score Probability="5" Impact="5" Color="#FF0000">72</Score></Scores><Source>7.82</Source><ScoreMethod>Highest</ScoreMethod></PID>
<SourceProjectID>-1</SourceProjectID>
<PlanData><TotalTaskCount>26</TotalTaskCount><InProgressTaskCount>0</InProgressTaskCount><CompletedTaskCount>0</CompletedTaskCount><TimeNow INTVAL="20191203">2019-12-03</TimeNow><DeterministicFinish INTVAL="20210824">2021-08-24</DeterministicFinish><TotalCost>208700.000000</TotalCost><ActualCostToDate>0.000000</ActualCostToDate><RemainingCost>208700.000000</RemainingCost><PrefCurrencySymbol>$</PrefCurrencySymbol><DecimalPlaces>0</DecimalPlaces><DecimalSeparator>.</DecimalSeparator><ThousandSeparator>,</ThousandSeparator><FileName>C:\Users\Jacqu-ee\OneDrive\NEU - Work\PJM Assignments\PJM6015 Assignments\PJM6015_Project Risk Management_2020-2021\Risk Register Sample Plan.plan</FileName><Title>Risk Register Sample Plan.plan</Title></PlanData>
2.1
[AdditionalInfo]
RiskCurProbCol | 4
RiskCurScoreCol | 8
RiskTarProbCol | 12
RiskTarScoreCol | 16
MitActPostProbCol | 13
MitActPostScoreCol | 17
RiskUserFieldOneCol | 30
RiskUserFieldTwoCol | 34